## CSR New Projects
TERP NEW PROJECTS | Contract Amount | Change Orders | CSR Cut-off Date | CSR Presentation | Accomplishment (%) |  | Projected Net Contract Amount | Cost Status Report | Projected Profit (Contract Amount - CSR) | Remarks
[5 empty] | Billed | Actual
1.0 Jun David | 561326636.24
1.1 JIL Tower
1.1.1 Structural Works Package 1 | 72000000 |  |  |  |  | 58.91%
1.1.2 Retrofitting Works Package 2 | 42448917.24 |  |  |  |  | 76.08%
1.1.3 Retrofitting Works Package 3 (For zone 1 using steel jacket) | 49400000 |  |  |  |  | 38.74%
1.1.4 Electrical roughing - ins works | 540000 |  |  |  |  | 48%
1.1.5 Controlled Demolition Works | 1437719 |  |  |  |  | 34.23%
1.2 Woodsville Crest Residences
1.2.1 Woodsville Tower 3 | 276000000 |  |  |  |  | 40.45%
1.2.2 Woodsville Site Development | 54500000 |  |  |  |  | 49.09%
1.2.2 Woodsville Tower 1 Architectural - Fitout Works | 65000000 |  |  |  |  | 36.61%
2.0 Ramel De Castro | 537320631.83
2.1 Sierra Valley Gardens Residences
2.1.1 Sierra Tower 4 | 439320631.83 |  |  |  |  | 31.54%
2.1.2 Sierra Tower 1 Fit - out works | 98000000 |  |  |  |  | 55.2%
3.0 Godfrey Aranzaso | 1049051525.1
3.1 Great Valley Medical Center
3.1.1 Great Valley Medical Center Architectural | 640000000 |  |  |  |  | 14.72%
3.1.2 Great Valley Medical Center Phase I 12-15Fa | 126000000 |  |  |  |  | 98.9%
3.1.3 Great Valley Medical Center Phase II 12-15Fb | 101000000 |  |  |  |  | 76.9%
3.2 Tarlac Hall of Justice | 182051525.1 |  |  |  |  | 99.42%
4.0 Alfhie Masinadiong
4.1 One Tolentino East Residences | 499000000 |  |  |  |  | 81.29%
4.2 One Tolentino East Residences - Sealant Application | 7200000 |  |  |  |  | 42.75%
4.3 One Tolentino East Residences - Precast Exterior Wall (125 MM THK) | 66145185.91 |  |  |  |  | 63.49%
4.4 One Tolentino East Residences - Sealant & P.U Foam Application (Interior Wall) for Tower 1 | 7700000 |  |  |  |  | 75.04%
4.5 One Tolentino East Residences - RSB Fabrication for Tower 2 | 1800000 |  |  |  |  | 63.32%
4.6 One Tolentino East Residences - Lintel Beam & Siffener Column for Tower 1 | 6800000 |  |  |  |  | 83.39%
5.0 Ryan Legaspi
5.1 Mantawi Residences - Cebu | 1550000000 |  |  |  |  | 18.21%
6.0 Mark Tumpalan | 339052142.2
6.1 Philsouth Projects - Dumaguete
6.1.1 Dumaguete Medical City | 219000000 |  |  |  |  | 34.42%
6.1.2 Dumaguete Government Center | 81552142.2 |  |  |  |  | 99.81%
6.1.4 Four - Storey Parking building | [5 empty] | 62.27%
6.1.3 Koko Hotel Dumaguete | 38500000 |  |  |  |  | 93.88%
7.0 Reymark La Guardia
7.1 Amisa Residences - Interior Painting Works | 25000000 |  |  |  |  | 11.07%
8.0 Giselle Gerardo
8.1 Lolo Uweng Phase 2 + existing contract (discuss with giselle) | 28080020.08 |  |  |  |  | 87.42%
8.2 Belfry Tower - Sacred Heart Parish Muntinlupa | 15332945.52 |  |  |  |  | 14.69%
9.0 Dolphy Esteban
9.1 FIli Bridgetown - Service Elevator ABWF | 8800000 |  |  |  |  | 91.75%
9.2 Grand Summit Pangasinan | 198000000 |  |  |  |  | 4.18%
10.0 Rowell Clarin
10.1 Maribago Mercado Resort | 102000000 |  |  |  |  | 0%
Gross Contract Amount | 5002609086.88
5% Tax | 250130454.344
Contract Amount After Tax | 4752478632.536
15% Profit of Gross Contract Amount | 750391363.032
Target Direct Cost | 4002087269.504